## Decisions
ID | Area | Decision | Options | Recommended | Why | Impact | Needed by | Status | Owner | Notes
D1 | Product | What "AI" means in Grocerai | (a) Deterministic engine + curated recipes (b) LLM generates each user's plan and recipes on request (c) Hybrid: LLM drafts recipes offline into the corpus, engine plans | (c) Hybrid | Predictable nutrition and cost, testable, no per-request AI spend. The LLM still grows the recipe corpus fast. | High | Phase 0 | Open
D2 | Product | Headline value: savings or health | Savings-led Health-led Equal weight | Savings-led; health is the reason to stay | Euros are measurable and shareable. The prototype already works this way, and savings is the number we can prove in beta. | High | Phase 1 | Open
D3 | Data | Where prices come from | Scrape retailer sites + leaflets Retailer partnerships Crowdsourced Buy from a data vendor | Scrape + leaflets now; pursue partnerships in parallel | The only source that works on day one. Needs a legal review of each chain's terms before phase 2. | High | Phase 2 | Open
D4 | Frontend | App platform | Expo (React Native) Flutter PWA Native Swift + Kotlin | Expo (React Native) + TypeScript | Phone-first product with store presence. One TS codebase for iOS, Android and the web demo; shares the engine and types with the API; OTA updates. | High | Phase 0 | Open
D5 | Backend | Language and runtime | TypeScript (Node) Python Go | TypeScript for API and engine; Python for ingestion only | One language between app and API so the engine is shared. Python where scraping, PDF and embedding libraries win. | High | Phase 0 | Open
D6 | Backend | Architecture style | Modular monolith Microservices Serverless functions | Modular monolith + one worker | Two developers. Module boundaries give ownership without operational cost. | High | Phase 0 | Open
D7 | Data | Database | PostgreSQL on Supabase Firebase (Firestore) MongoDB Atlas | PostgreSQL + PostGIS on Supabase, EU (Frankfurt) | Relational data with price history and store geography. Auth and storage bundled. EU residency. | High | Phase 0 | Open
D8 | Backend | Auth provider | Supabase Auth Clerk Firebase Auth Custom | Supabase Auth | Bundled with D7. Apple and Google sign-in, EU region, no passwords in our code. | Medium | Phase 3 | Open
D9 | Infra | Hosting | Supabase + Fly.io AWS Vercel + Neon Hetzner VPS | Supabase (DB, auth, storage) + Fly.io (API, worker), Frankfurt | Near-zero operations, EU regions, under 100 EUR a month through beta. | Medium | Phase 2 | Open
D10 | Backend | ORM and migrations | Drizzle Prisma Raw SQL | Drizzle | Close to SQL, light, good TypeScript types, migrations from CI. Low impact either way. | Low | Phase 2 | Open
D11 | Architecture | Where the engine runs | Device only Server only Shared package, runs on both | Shared pure TypeScript package, runs on device and server | Instant offline interactions on the phone. Server run for the Thursday rebuild and a push that says a number. | High | Phase 0 | Open
D12 | Frontend | Maps and routing | MapLibre + OSM + OSRM Mapbox Google Maps | MapLibre + OSM tiles; straight-line distance now, OSRM later | Free, no lock-in. Route quality is not the early bottleneck. | Low | Phase 1 | Open
D13 | Data | Nutrition data source | USDA FoodData Central Open Food Facts OPKP (Slovenian) Manual entry | OPKP or USDA for generic ingredients; Open Food Facts for branded products later | Free and covers the recipe ingredients. Branded data improves accuracy once products are matched. | Medium | Phase 1 | Open
D14 | Content | Recipe corpus | Hand-curated Licensed from a publisher LLM-generated with review | About 100 hand-curated; LLM-assisted drafting, dietitian review | Quality and liability. Below roughly 100 recipes, weeks repeat and users churn. | High | Phase 1-4 | Open
D15 | Data | Product matching approach | Rules only Embeddings + LLM + human review Fully manual | Embeddings + LLM classification; review queue below a confidence threshold | Scales across chains; matching memory shrinks the review load every week. Scoped to the ~40 recipe products, not full catalogs. | High | Phase 2 | Open
D16 | Frontend | Offline strategy | Online only Cache the current week Full local-first sync engine | Cache the current week; shopping mode fully offline | Aisles have no signal. A full sync engine is overkill for one device per trip. | Medium | Phase 1 | Open
D17 | Product | Is an account required? | Required up front Optional; local-only mode is complete Required after the first week | Optional; the app is complete without one | Lowest onboarding friction and matches the local-first phase 1. An account adds sync, history and push. | Medium | Phase 3 | Open
D18 | Legal | Body metrics as health data | Treat as GDPR Art. 9 special category (explicit consent, EU only, skippable) Treat as ordinary personal data | Special category | Weight, goal and allergens are health data. Retrofitting consent and residency later is expensive. | High | Phase 1 | Open
D19 | Repo | Monorepo or multi-repo | Monorepo (pnpm + Turborepo) Separate repos per app | Monorepo | Shared engine and contracts. Two developers, one PR flow, one CI. | Medium | Phase 0 | Open
D20 | Ops | Analytics and error tracking | PostHog EU + Sentry Firebase Analytics + Crashlytics Nothing until beta | PostHog EU + Sentry | EU-hosted, free tiers cover beta, and it is how we validate the savings claim. | Low | Phase 1 | Open
D21 | Go-to-market | Launch geography | Ljubljana only All of Slovenia Slovenia + neighbours | Ljubljana beta | Store geography and price coverage stay manageable. The prototype already assumes it. | Medium | Phase 4 | Open
D22 | Product | Web scope | Landing page + wizard demo Full web app Mobile only | Landing page + wizard demo from the Expo web build | Nearly free from the same codebase. A full web app adds little for in-store use. | Low | Phase 1 | Open
D23 | Business | Monetisation | Free Subscription Retailer-paid placement Affiliate | Defer until beta; instrument savings now | Pricing should be set against measured savings. Per-user cost is near zero, so every model stays open. | High | Phase 4 | Open

## Legend
How to use | One row per decision. Pick an option, set Status to Decided, add your name and the date in Notes. If you deviate from the recommendation, say why in Notes so the architecture doc can be updated.
Status
Open | Not decided yet.
Decided | Chosen; the architecture doc reflects it (or a PR is open to update it).
Deferred | Consciously postponed; the plan proceeds on the recommended option until revisited.
Impact
High | Changes the shape of the system or the product. Expensive to reverse after the phase it is needed by.
Medium | Changes one component or a phase's scope. Reversible with moderate rework.
Low | Local choice. Swappable later at small cost.
Needed by
Phase 0 | Decide and scaffold (1 week).
Phase 1 | Local-first app on the seed catalog (4-5 weeks).
Phase 2 | Real prices: ingestion, matching, catalog bundles (5-6 weeks).
Phase 3 | Accounts, sync, Thursday rebuild and push (3-4 weeks).
Phase 4 | Ljubljana beta (ongoing).
Source | docs/architecture/README.md, frontend.md, backend.md, roadmap.md on branch Aljaz/app-architecture. Draft v0.1, 11 Sep 2026.